UNIVERSITY OF CALGARY

ENGO 500: GIS and Land Tenure #2
Technical Deliverables Report

By:	Jeremy Steward
	Kathleen Ang
	Ben Trodd
	Harshini Nanduri
	Alexandra Cummins
Supervisor:	Dr. Steve Liang

DEPARTMENT OF GEOMATICS ENGINEERING

SCHULICH SCHOOL OF ENGINEERING

2013-12-06
# Introduction
## Purpose & Scope
The purpose of this document is to summarize and describe the progress of group GIS & Land Tenure #2, in particular to report the development of an open-source Internet-of-Things initiative. This report describes in detail the work done by the group with regards to the planning process of the project, the development of a prototype smart-shelf as part of the project design, and the development of a user-friendly web-based interface with which to interact with our shelf prototype.
Upon completion of describing the work done thus far in the project lifetime, the project schedule and timeline is evaluated. Milestones accomplished and problems encountered are discussed and evaluated, and finally a risk-assessment for the future of the project lifespan is considered. A final summary of the project status is stated, followed by a brief conclusion on the work done and goals to strive for in the remaining life of the project.
## Project Overview
The particular focus for this project is about the concept of “Internet of Things”. The Internet of Things (IoT) is a scenario in which objects, animals or people are provided with unique identifiers and the ability to transfer the data automatically over a network without requiring human-to-human or human-to-computer interaction [1]. The Internet of Things, while barely known within the common vernacular, is an interesting concept in that it suggests a world where information about the real world can be directly interacted upon through common interfaces (in this case, the internet).
The number of IoT applications are expected to rapidly increase in the future, and likewise drive tremendous value for both businesses and people [x]. However, a budding problem within the IoT ecosystem is that for any given object connected to the IoT, we find that there often exists implementation specific methods. Similar to how HTTP unified the web, part of this project focuses on implementing an Internet of Things application in a standards-compliant fashion, to reduce the amount of intellectual overhead for developers who wish to learn how to interact and develop the IoT platform, as well as provide users a common gateway for IoT devices that they can trust.
To this end, our primary objective for this project is to develop an application that applies Internet of Things concepts in order to serve as an example for future Geomatics professionals and developers to create location-aware services, and likewise to assist in pushing forward the IoT SWG standard [x] proposed by the Open Geospatial Consortium (OGC). OGC standards are technical documents that specify interfaces and/or encodings. Software developers use these documents in order to build open, accessible interfaces and encodings into their products and services [2]. Given these objectives for our project, two explicit requirements were set:
1. Develop a hardware prototype of some sensor setup that uses the Internet of things, and interface it with some web-based software system using the OGC IoT SWG standard [x].
2. Develop this application as Free, Open-Source Software (FOSS), such that anybody can access the code and tweak, develop, mashup, and redistribute it past the lifespan of the project.
From these, our group was given freedom to plan and manage what kind of project we wished to develop.
# Project Conceptualization and Planning
Given the above stated goals of our project, our team was given free-reign over what type of solution we believed would be a good fit to act as both a proof-of-concept and working implementation of an Internet of Things application. It was important to consider that our project would not only act as an example case for the upcoming OGC IoT standard, but we also wished to design something that would have impact, and hopefully be useful in some aspect.
That said, much time was devoted to determining an appropriate application with which to apply IoT principles to produce a solution. For the majority of the first six to eight weeks of development, serious consideration went into specifically defining and refining our project scope and definition. Most of this progress has been consolidated into an appropriate literature review [x], which likewise defined both our prototype and web-interface specifications, as well as proved to show that our project would have impact and provide value to store clerks and managers who would be the primary target of our developed solution [xx][xxx].
Upon determining our project scope and purpose, a use case analysis was conducted. A use case study is done to define interactions between a system and an actor or actors to achieve a goal. This is a high level-planning tool to help develop requirements. It was chosen as a first step in development due to its precedence in modern software engineering as well as its ability to evolve with the project.
The first step taken was to create a use-case or class-interaction diagram. Creating a visual overview of the system helped to define what functionality the final system would support. Figure 1 shows this Use-Case diagram:

# Location-Aware Smart Shelf (LASS) Prototype

# Web-Based Interface for LASS
The key word that many take away when imagining the Internet of Things is the internet. The internet has exploded in use and popularity in recent years, and plays an important part in information exchange. Therefore, as a corollary to our LASS prototype which takes measurements in from attached sensors, we are likewise developing a web-based user interface with which to interact with our shelf systems. This interface will exist as a website where targeted users can log in, view, and interact with the hardware through their web browser.
## Specifications
The following two lists of functional and non-functional specifications were compiled in our previous literature review [x] for our website design. These specifications seek to define the direction with which our final product will be developed.
### Functional
1. The ability to view shelf facings in real time, and determine where products in the store need to be restocked.
2. The ability to track customers entering and exiting each respective aisle, and determine how long each customer stayed in that section of the store.
3. The ability to generate some basic analytics based on data from the sensors. This can include items such as determining hotspots or busy times around the store, analyzing which parts of the store are more popular (most shelves empty), and other organizational information, such as busy times within the store, or average time left un-faced.
### Non-Functional
1. The system should be painless and simple to introduce. Specifically, it should not require the user to do anything beyond setting up the hardware. For this reason, a central website that distributes management of multiple entities is preferred to a more decentralized system, where entities would set up their own specialized hardware for their application.
2. The system should be secure and prevent unauthorized entry. This is to protect consumers from privacy concerns, as well as to protect both managers and the data server from malicious entities.
3. The system should be robust enough that events such as power loss or switching products between shelves should not produce any significant overhead to the system.
4. The system should be easy to manage and should provide managers with the ability to readily pull up any information from a given store or branch that they might choose.
5. The system should have received an extensive amount of testing, preferably upwards of 30 hours of actual use testing and bug-fixing. As the project expands the test requirements will also be expanded to maximize ease-of-use of the final product.
6. All of the software should operate using the OGC IoT SWG standard, and should be published as free, open-source software for anyone to access and improve upon.
## Completed Work-to-Date
Aside from the above listed specifications, and the aforementioned use-cases describing the interactions of the system as a whole, other work has been started in the interest of rapidly developing the web-based interface of our project. In particular, research regarding web technologies and frameworks have been progressing far ahead of schedule, thanks in part to splitting the team and using a divide-and-conquer approach for the remainder of the project milestones.
With regards to research, the website team has decided to develop the final system using the following popular, established web technologies:
- HTML + CSS + Javascript
- Bootstrap [x] for dynamic CSS
- jQuery [x] for dynamic animations and effects in our user interface (UI)
- D3JS [x] for visualization of our sensors
Of the above, the website team has already learned and become comfortable with HTML, CSS, and Javascript as development languages, and jQuery as a standard development library. Thus, much of the research for implementing the website is done, all that remains is to learn the remaining two technologies (Bootstrap and D3JS) and implement our use cases as defined in Appendix B.
### Technical Demo of OGC Database Interaction
To show off the progress made in understanding the OGC IoT SWG database, and to show off an example of how measurements are to be read off of the server from live data, a small technical demo page was created with a small number of interactive elements to show live data being read from the server in real-time. An example of this page can be seen in Figure 1 below:

Figure 1:An example of the web page rendered before user interaction

From the above webpage, clicking on the orange button shown above yields the following data-streams pulled from the provided server, seen in Figure 2:

Figure 2: Dynamic loading of observation content (descriptions of data-streams shown)
While not directly applicative to the end goals of our interface, this example shows our progress in pulling data directly from the server, which is incidentally one of the larger hurdles in accomplishing our end goal. The full code can be found on the group Github repository [x], or can be seen at http://jsfiddle.net/XkBAm/1/.
# Schedules, Risks and Status
The project has gone through a significant change from the original forecasted schedule of events. This was primarily due to a lack of experience in design, development procedures, and project management within the team. Although the tasks completed did not align well with the original timeline found in the project proposal, the team remains confident that the goals of the project will be met by the final deadline.
The biggest mistake in the projected project velocity was in identifying and estimating the initial stages of the project. With a loosely defined project statement, the team spent a considerable amount of time deciding on an application for which an IoT solution was appropriate. The tasks thats followed, such as deciding on which micro-controller to use, which sensors to use, what website framework to work with and learning the OGC’s proposed IoT API were all time consuming tasks that had originally appeared to be small amounts of work in terms of technical deliverables. However, they did result in a greater knowledge and understanding of each of the components that make up the project, as outlined in the preceding section. These were not all anticipated steps, and thus, are not shown in the original Gantt Chart.
Although the team had planned on doing the project in two phases, hardware development followed by website development, this plan was deviated from. At week 8, the team decided to split into a team of three working on hardware implementation, while a team of two began work on the product’s website. This made a considerable change to the timeline of the project.
Examining the Gantt Chart form the project proposal shows that the following milestones in Table 1 below were projected to be done by December 6th:
Table 1: Milestones to be completed before end of term (December 6th)
Milestone	Status	Comments
Determine location based application	Complete	The application chosen was Location Assisted Smart Shelf (LASS)
Design sensor setup - Determine technical requirements - Acquire Sensors / - Create prototype - Test prototype	Complete Started Not started Not started	The technical requirements were determined as part of the deliverables for the literature review. The required sensors have been sent for approval but not acquired.
API-Sensor interface - Research into languages/specifications - Collect test set of data	Complete Not Started	While the language and specifications have been researched, having not purchased sensors leaves this task unfinished.
Project Proposal	Complete
Literature Review	Complete
Technical Deliverables - Written Report - Oral presentation	Complete Complete

The following milestones in Table 2 were projected to have been started by December 6th:
Table 2: Milestones to have been started by end of term (December 6th)
Milestone	Status	Comments
Create Library to interface with database	Started	Using simulated data, information has successfully been PUT to the database

Table 3 below depicts milestones that were projected to begin after December 6th, but have been begun development due the introduction of a split team focus:

Table 3: Milestones projected to being at the start of the second term, but have already been started
Milestone	Status	Comments
UI Development - Research required frameworks - Create prototype of UI - Attach to database - Test UI - Polish / Revise UI - Create video of UI in use	Complete Not Started Started Not Started Not Started Not Started	Progress to date focused on learning website development, and interfacing with the database. A mock website was created, but UI development has not yet begun.

Lastly, we can see Table below, which describes milestones and sub-tasks that were not initially predicted, but were completed before December 6th:
Table 4: Milestones not initially accounted for but have been completed or are in progress before the end of term (December 6th)
Milestone	Status	Comments
Define Use Cases - Hardware Use Case Diagram / - Hardware Use Cases - Website Use Case Diagram - Website Use Cases	Started Started / Started Started	While the Use Cases attached in Appendix A and B at the end of the report are mostly complete, they have yet to be finalized by our supervisor, and some additional ones remain to be added at this moment in time.
Learn web development fundamentals - HTML / - CSS - jQuery	Complete Complete Complete	This milestone was for the two team members focused on web development.
Learn introductory Python programming	Complete	This milestone was for the three team members focused on hardware development
Explore and understand database structure and commands	Complete
Create demonstrative proof of concept - Post data to server - Display data on website	Complete Complete	This milestone was done for the oral presentation

Due to the large change in the project direction, a new Gantt chart has been created. The time that has passed now reflects the project milestones that have been accomplished thus far, and a re-evaluated version of the future milestones can now be seen past week 12. This Gantt chart can be seen in Figure 3, on the following page:

Figure 3: Updated Gantt chart of project timeline. Current time is marked by the solid gray bar, tasks that have been set back are marked in maroon.
Looking at the original Gantt chart seen in the proposal [x], this one has several differences, most notably in that it is far less vague and is more specific with the project requirements and scope, which have been more properly been defined since that time. The major differences are:
- The original Application Design section was expanded to the new Project Conceptualization & Planning section, which lays out several sub-tasks within the milestone, including:
  - Research into the value of chosen application
  - Research applicable sensors
  - Produce specification sheet(s)
  - Develop and flesh-out our class (UML) model diagrams.
  - Build use-cases to define the structure and interactions between our software elements
- The Design sensor setup sub-task has been split from the planning phase of the project, and more appropriately placed into the Application Prototype Development section. The sub-tasks of this milestone have likewise been merged with the API-sensor interface milestone, since a large portion of the work done in creating our prototype will revolve around ensuring that our prototype can properly communicate with the provided OGC IoT database.
- The website development has been consolidated, and proper testing steps (including a usability survey) have been added as sub-tasks.
## Potential Risks
Some of the potential challenges we risk running into can be summarized in the following list:
1. Given that we have delayed ordering sensors until really late, we potentially run the risk of losing much of our time waiting for the sensors to ship. Our application prototype currently allots for some time to be lost (see Figure 3), however, there is only approximately a three week window where this is acceptable. Should the sensors be delayed by more than three weeks (from their regular shipping time, 4-6 weeks), there may be serious consequences to the final leg of our development. To mitigate this, we are using the inputs and outputs specified by our use-cases to simulate data read in from the sensors we currently do not have. In this way, we should still be able to make a functioning system, which should allow other pieces of the system to interact even if the physical sensors themselves are missing.
2. Since our group has split into two teams, one focused on developing the prototype, and the other focused on developing the web-based interface, we run the risk of developing orthogonal to each other's work. In this case, we require strict definition and adherence to our use cases in order to avoid running into a situation where the input of one of our components is not coherent with the remainder of our system. In this way, by mitigating this risk, we also save ourselves from code duplication, and prevent ourselves from running in circles re-writing modules and objects.
3. One significant challenge during this term was gaining some momentum within the project, specifically because much of the legwork this term favoured planning, careful research, and conceptualization over hard deliverables. This resulted in appearing to have very little done on the surface, while having established a reasonable framework through our use-cases and documentation with which to develop our project further. Given that there are a larger number of breaks in the winter term (Christmas break, Reading week, Easter, etc...), we run the chance of losing our momentum and potentially falling behind. What's more, with this being the last term before (hopefully) graduation for the group, there is a chance that work from prioritizing other classes and electives constitutes a significant barrier to getting work done fluidly and efficiently. For this reason, a more stringent time input will likely be enforced in the new term, and expectations for weekly output will attempt to be measured to some standard. Moreover, much of the work into the finalization and development of our use-case modules will attempt to be done over these breaks, to try and mitigate the otherwise demanding nature of engineering.
4. One risk that was not fully explored in this document or in others we have published regard that of cost. It is assumed until this point that our prototype will be built, but little thought has been given to cost aside from ordering the sensors. This is a significant risk in that if we want our final product to be successful and have impact, we need to worry about the cost of the final device and the associated ease-of-use and value it provides. The value itself has been explored within our previous Literature Review [x], but has not necessarily been weighed against the cost of individual sensors (or that of mass-produced products, which would likely bring about better results). Part of the final report should perhaps explore what was learned with regards to the number of sensors required for effective testing, and what the lower limits are in terms of cost reduction.
## Project Status

# Conclusion

# Appendix A: Hardware Use Cases
# Appendix B: Software Use Cases

# References